## Sheet1
ITEM | Probability | Impact | RISK | Mitigation | Residual Risk
1) Data compromised causing client reputational risk | Moderate | Extreme | HIGH | 1) Encrypt data at rest and in transit | LOW
2) Anaonomize sensitive data
3) Keep data on secure server
2) Requirements may be late or incomplete | Likely | Major | HIGH | 1) Establish hard "freeze date"
|  |  |  | 2) Prioritize for scope reduction | MEDIUM
3) Tools are immature or have steep learning curve | Moderate | Major | MEDIUM | 1) Establish cutoff date for new tools | LOW
2) Use tools that are well known by team
4) Workload exceeeds time allowed for project | Likely | Moderate | MEDIUM | 1) reduce scope to fit available resources | LOW
2) Add staff
5) Datacenter or hardware failure causes loss of artifacts | Moderate | Extreme | HIGH | 1) Make sure all artifacts are backed up | LOW
2) use version control (eg. Github)
3) Make copies of work on separate servers